## Production Plan - Sprint One
Category | Priority (1-5) | Task | Date Added | Assigned To | High Est (In Hours) | Low Est (In Hours) | Actual Time (When Done) | Status | Notes
Document | 5 | Create proposal | 2023-02-08 | All | 5 | 4 | 5 | Done
Research | 4 | Research on Naive Bayes | 2023-02-08 | Kareem, Manasa, Varsha | 3 | 2.5 | 4 | Done
Research | 4 | Requirement Analysis | 2023-02-08 | Kareem, Vrushabh, Varsha | 4 | 3.5 | 4 | Done
Document | 5 | Flowchart | 2023-02-08 | Vrushabh, Alekhya | 4 | 3.5 | 3 | Done
Data | 5 | Find Dataset | 2023-02-11 | Alekhya, Manasa | 5 | 4.5 | 4 | Done
Meeting | 3 | Meeting(Zoom) | 2023-02-13 | All | 1 | 0.5 | 1 | Done
|  | HIGH |  | 21 | < Total High Est Column
|  | LOW |  | 18 | < Total Low Est Column
|  | AVERAGE |  | 19.5 | < Average of Total High and Total Low
|  | DONE |  | 20 | < Total Actual Time Column
|  | REMAINING |  | -0.5 | < AVERAGE - DONE
Graveyard of Cut Features

## Production Plan - Sprint Two
Category | Priority (1-5) | Task | Date Added | Assigned To | High Est (In Hours) | Low Est (In Hours) | Actual Time (When Done) | Status | Notes
Data | 4 | Data Analysis/Preprocessing | 2023-02-13 | Kareem, Varsha | 5 | 4 | 6 | Done
Data | 4 | Data Visualisation | 2023-02-15 | Manasa, Vrushabh | 5.5 | 5 | 5 | Done
Research | 3 | Research on SVM | 2023-02-17 | Alekhya, Varsha, Vrushabh | 6 | 5 | 5 | Done
Research | 4 | Research on Neural Network | 2023-02-17 | Kareem, Manasa, Varsha | 5 | 4.5 | 4 | Done
Meeting | 3 | Meeting(Zoom) | 2023-02-20 | All | 1 | 0.5 | 1 | Done
|  | HIGH |  | 22.5 | < Total High Est Column
|  | LOW |  | 19 | < Total Low Est Column
|  | AVERAGE |  | 20.75 | < Average of Total High and Total Low
|  | DONE |  | 21 | < Total Actual Time Column
|  | REMAINING |  | -0.25 | < AVERAGE - DONE
Graveyard of Cut Features

## Production Plan - Final Sprint
Category | Priority (1-5) | Task | Date Added | Assigned To | High Est (In Hours) | Low Est (In Hours) | Actual Time (When Done) | Status | Notes
Model | 3 | Create Model | 2023-02-21 | Vrushabh, Alekhya, kareem | 7 | 5.5 | 6 | Done
Model | 3 | Prediction/Validation | 2023-02-23 | Alekhya, Varsha | 6 | 4.5 | 6 | Done
Testing | 1 | Testing | 2023-02-25 | Varsha, Kareem | 5 | 3.5 | 4.5 | Done
Meeting | 3 | Meeting(Zoom) | 2023-02-27 | All | 1 | 0.5 | 0.5 | Done
Meeting | 4 | Creating the project progress video | 2023-02-27 | All | 2 | 1 | 1 | Done
Document | 3 | Additional enhancements to the project | 2023-02-27 | Manasa, Varsha, Alekhya | 3 | 2 | 3 | Not Done
|  | HIGH |  | 24 | < Total High Est Column
|  | LOW |  | 17 | < Total Low Est Column
|  | AVERAGE |  | 20.5 | < Average of Total High and Total Low
|  | DONE |  | 21 | < Total Actual Time Column
|  | REMAINING |  | -0.5 | < AVERAGE - DONE
Graveyard of Cut Features